## Adapters
Work stream | Dev1 | Dev2 | Buddy | Working Model | BA | Delivery Date | Requirements Block?
CAA OUT | Niall | Tim? |  | EMC lead + NE assist? | John | 2011-02-15 | LOW
NCL | Francois | Pierre | Nileesha | EMC lead | Graham | 2011-02-15 | LOW
NC IN MKT | Francois | Pierre | Nileesha | EMC lead | Graham | 2011-02-15 | LOW
NC IN TKT | Francois | Pierre | Nileesha | EMC lead | John | 2011-02-15 | MED
UI FRAMEWORK | Ravi |  |  | EMC | Gary | 2011-02-15 | MED
UBIX IN | Dhileep |  |  | EMC | Gary | 2011-02-15 | HIGH
TEO OUT | Scott |  | Niall | NE lead + buddy | Gary | 2011-03-01 | HIGH
NCR | Om |  | Addy | NE lead + buddy | Aash | 2011-03-01 | LOW
NPR | Dom |  | Addy | NE lead + buddy | Aash | 2011-03-01 | LOW
GMI GCM | Ravi |  |  | EMC | Samir | 2011-03-01 | HIGH
NC OUT | Fabrice |  | Nileesha | NE lead + buddy | Graham | 2011-04-15 | LOW
CV IN | Niall |  |  | EMC | John | 2011-04-15 | LOW

## UI
Complexity | Days Effort
0 | 0
1 | 3
2 | 5
3 | 10
4 | 20
| Task Name | Estimate: Functionality and Data Analysis | Estimate: UI (HTML/CSS) | Days UI | Estimate: Server-side Java development | Days Server Side | Estimate: Create test scripts
Home Page
| Navigation |  | 1 | 3 | 1 | 3
Trade Lifecycle Dashboard
| Main Screen |  | 4 | 20 | 2 | 5
Clearvision
| Low alert expanded view |  | 2 | 5 | 2 | 5
| High alert expanded view |  | 2 | 5 | 2 | 5
NewClear
| Low alert expanded view |  | 0 | 0 | 1 | 3
| High alert expanded view |  | 0 | 0 | 1 | 3
TEO
| Low alert expanded view |  | 0 | 0 | 1 | 3
| High alert expanded view |  | 0 | 0 | 1 | 3
CAA
| Low alert expanded view |  | 0 | 0 | 1 | 3
| High alert expanded view |  | 0 | 0 | 1 | 3
Newclear Lite
| Low alert expanded view |  | 0 | 0 | 1 | 3
| High alert expanded view |  | 0 | 0 | 1 | 3
GMI
| Low alert expanded view |  | 0 | 0 | 1 | 3
| High alert expanded view |  | 0 | 0 | 1 | 3
Adapter-level Break Summary (all trades)
| Main Screen |  | 3 | 10 | 4 | 20
| Compare Trades |  | 2 | 5 | 2 | 5
Break Detail View (messages for a trade)
| Main Screen |  | 2 | 5 | 2 | 5
| Filter Options for Break Detail View |  | 2 | 5 | 2 | 5
| Advanced Search Options Sidebar |  | 2 | 5 | 0 | 0
| Advanced Search Options Criteria |  | 2 | 5 | 0 | 0
| Return Search Results |  | 0 | 0 | 4 | 20
| Message Detail View (FIX for a message) |  | 3 | 10 | 1 | 3
Resubmit
| Resubmit Single Trade Overlay |  | 1 | 3 | 1 | 3
| Resubmit Single Trade Confirm Overlay |  | 1 | 3 | 1 | 3
| Resubmit Mulitple Trades Overlay |  | 1 | 3 | 1 | 3
| Resubmit Single Trade Confirm Overlay |  | 1 | 3 | 1 | 3
Overwrite
| Overwrite Single Trade Overlay |  | 1 | 3 | 2 | 5
| Overwrite Single Trade Confirm Overlay |  | 1 | 3 | 2 | 5
| Overwrite Multiple Trades Error Overlay |  | 1 | 3 | 2 | 5
KPI
| Trade Volumes |  | 2 | 5 | 3 | 10
| Trade Volumes Filter Criteria |  | 2 | 5 | 3 | 10
IT
| Trade Lifecycle Dashboard |  | 2 | 5 | 2 | 5
| Set Volume Alerts |  | 2 | 5 | 2 | 5
RULES EDITOR
| TBC |  | 4 | 20 | 4 | 20
ADMIN
| TBC |  | 3 | 10 | 4 | 20
|  |  | Days | 149 |  | 203